ASRS
1. Project Planning
2. Concept Generation
3. Preliminary Design
4. Final Design
5. Presentation
1.1.
Code Of Conduct
1.2.
Stakeholder Requirements
1.3.
Product Design Specifications
1.4.
Work Breakdown Structure
1.5.
Gantt Chart
2.1.
Research
2.2.
Generation
2.3.
Simple CAD Models
2.4.
Selection And Refinement
3.1.
Calculations
3.2.
Part/Material Selection
3.3.
Drive System Selection
3.4.
CAD Prototypes
4.1.
Design Choices Documentation
4.2.
CAD Models And Drawings
4.3.
Calculation Documentation
5.1.
Final Design Document
5.2.
Presentation Slides
5.3.
Presentation Oral

---
ASRS
1. Frame
Benjamin Jacobs
1.1. Product Design Specifications
1.2. Concept Generation and Selection:
- Integration of subsystems
- Connection types
1.3. Material/Part Selection
1.4. Calculation and CAD Documentation
1.5. Subsystem Presentation
2. Translation (x)
Stacy-lee van Schalkwyk
2.1. Code of Conduct
2.2. Concept Generation and Selection:
- Actuation System
- Rail interface
- Shaft design
2.3. Material/Part Selection
2.4. Calculation and CAD Documentation
2.5. Subsystem Presentation
3. Extension (y)
Elias Joubert
3.1. Work Breakdown Structure
3.2. Concept Generation and Selection:
- Actuation System
- Pallet interface
3.3. Material/Part Selection
3.4. Calculation and CAD Documentation
3.5. Subsystem Presentation
4. Elevation (z)
Sarah van der Walt
4.1.1. Gantt Chart,
4.1.2. Stakeholder Requirements
4.2. Concept Generation and Selection:
- Actuation System
- Guiding Mechanism
4.3. Material/Part Selection
4.4. Calculation and CAD Documentation
4.5. Subsystem Presentation